## Sheet1
Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
Create an account | As a user I want to enter a username/email/phone number and a password so that I can use the application. | High | TRUE | 1 | To be started
View resturants | As a user I want to view all available resturants so that I've freedom to choose from them. | High | TRUE | 1 | To be started
| As a user I want to view nearby resturants so that I can recieve the order faster. | Medium | TRUE | 1 | To be started
| As a user I want to view resturant clients reviews so that I have a higher chance of having a perfect meal. | High | TRUE | 1 | To be started
Search resturants | As a user I want to search for resturants based on name/location/reviews/availability/category so that I can order faster. | High | TRUE | 1 | To be started
View menu | As a user I want to view the resturant menu items and each item details such as price, ingredients so that I can pick my favourite items. | High | TRUE | 1 | To be started
Add to cart | As a user I want to be able to add items to my shopping cart so that I can place the order | High | TRUE | 2 | To be started
Purchase | As a user I want to be able to add a payment card so that I can pay online. | High | TRUE | 2 | To be started
Restaurant views order | As a resturant I want to able to view orders so that I choose to accept it or not. | High | TRUE | 3 | To be started
Restaurant marks order as delivered | As a resturant I want to able to mark orders as delivered so that the user can review the order. | High | TRUE | 3 | To be started